## Ark1
Project Plan (V2 - 19-09-2022): String indexing with compressed pattern problem
Week | Implementation | Thesis | Reading
1 | LZ77, Suffix Array & Tree, Phrase Trie V1 |  | Section 3
2 | Phrase Trie V2 (Linear space) |  | Section 4
3 | Preprocessing: RMQ, LCP |  | **
4 | Fix preprocessing |  | Generalized Substring Compress. (GSC)
5 |  | Preliminaries (ST, LZ77) | ST + LZ77 Material
6 |  | Review section 3-4 + found details
7 |  | Review RMQ + found details
8 | Fall Break | Fall Break | Fall Break
9 |  | Review GSC + found details | Section 5+6
10 | Improve Phrase Trie (V3) [in practice]
11 |  | Review section 5
12 |  | Review section 6
13 | Testing, gather data, figures
14 |  | Results
15 |  | Conclusion, introduction, abstract, etc
16 |  | Proof reading, final touches
17 | ? | ? | ?
18 | ? | ? | ?
19 | ? | ? | ?
20 | ? | ? | ?
* When refering to sections, it is a reference to sections in "String indexing with compressed patterns".
** Theoretical and Practical Improvements on the RMQ-Problem, with Applications to LCA and LCE
*** found details = details which were found when implementing
?: Will be used as buffers, probably being more implementation iterations / documenting implementations